## Project Info
ĐẠI HỌC KHOA HỌC TỰ NHIÊN KHOA CÔNG NGHỆ THÔNG TIN CQ – HK1 – 2k9 – 2k10
LUẬN VĂN TỐT NGHIỆP Chuyên ngành công nghệ phần mềm
Project Name : LMS System
Framework : JPOS | Date start : 21/7/2009
Project Owner :
Phạm Thế Hùng
Nguyễn Khuyến
Technical Support : JPOS team
Professor Guide : Trần Hiển Đạt
University : University of science

## Document
Document process tracking
Filename | Description | Notes
ArchitectureDesign
CoCheBienDichCuaJPos
CRM_LMS_ActualState And Solution
jpos tren LINUX
QSP và Q2
SequenceDiagram
spec
Tescase Loyalty Manage System
ThietKeDuLieu
Tìm hiều về chuẩn ISO8583
transaction
usercase model
vision

## Database
Database process tracking
Task ID | Task Name | Description | % Completed | Notes | Date | Issue | Owner
1 | Create draft for Database | Create draft for new requirement of project , draw a new diagram of database, add more field to table, take note for each table | 100% | Some table need more field to add, but I don't have any idea to add field | 2010-04-09 |  | Nguyen Khuyen
2 | Review Database | Review database and apply it to System |  |  |  |  | Pham The Hung
3 | Create document report for Database | Create document report for database, capture picture of database diagram in SQL server |  |  |  |  | Nguyen Khuyen
4 | Generate Script from Draft | Create Script for SQL server |  |  |  |  | Nguyen Khuyen
5 | Verify Database performance | Verify performance of database in real time |  |  |  |  | Nguyen Khuyen
6 | Modify Database | Modify database to run stably |  |  |  |  | Nguyen Khuyen